## Dashboard
Our Story - Project Control Dashboard
Target birthday | 2026-08-08 |  | Open items
P0 scope freeze | 6 August 2026 18:00 IST |  | P0 backlog total
Primary device | Mobile phone - portrait |  | P0 backlog done
Current release status | Planning / content intake |  | Release blockers
Release gate | Owner | Status | Evidence / notes
Content approval | Client / Project Owner | Not Started
Engineering P0 | Orchestrator | Not Started
Privacy/security | Security Reviewer | Not Started
Real-device UAT | QA / Client | Not Started
Production verification | Release Owner | Not Started
Retirement scheduled | Project Owner | Not Started

## Open Items
ID | Item | Owner | Status | Due Date | Decision / Answer | Affected Requirement IDs | Notes
OI-01 | Recipient name, exact spelling, nickname, and preferred salutation | Client / Project Owner | Open
OI-02 | Sender name, nickname, and final signature | Client / Project Owner | Open
OI-03 | Domain/subdomain and launch URL | Client / Project Owner | Open
OI-04 | Final access policy: private link, passphrase, or managed protection | Client / Project Owner | Open
OI-05 | Final birthday letter and exact on-screen copy approvals | Client / Project Owner | Open
OI-06 | Final media files, chronology, captions, and consent/rights confirmation | Client / Project Owner | Open
OI-07 | Voice-note file and approved transcript/caption | Client / Project Owner | Open
OI-08 | Background music selection and evidence of usage rights | Client / Project Owner | Open
OI-09 | Exact list of reasons, memories, inside jokes, and future dreams | Client / Project Owner | Open
OI-10 | Whether content may remain online after the birthday and deletion date | Client / Project Owner | Open

## Backlog
Task ID | Title | Priority | Owner Role | Dependencies | Status | Requirement IDs | Target Date | Evidence / Handoff
GOV-001 | Initialize private repository, CI, branch protection, ignored private paths | P0 | Orchestrator | - | Not Started
ARCH-001 | Implement typed content schema and build validation | P0 | Frontend Platform | GOV-001 | Not Started
ARCH-002 | Implement story reducer and transition tests | P0 | Frontend Platform | GOV-001 | Not Started
SEC-001 | Select and implement server-side access model | P0 | Security | GOV-001 | Not Started
MEDIA-001 | Create inventory and derivative pipeline | P0 | Media | ARCH-001 | Not Started
AUDIO-001 | Implement global media coordinator | P0 | Frontend Platform | GOV-001 | Not Started
UX-001 | Implement tokens, shell, safe areas, primitives | P0 | UX/Frontend | GOV-001 | Not Started
FEAT-001 | Start, welcome, birthday state | P0 | Feature | ARCH-002,UX-001,AUDIO-001 | Not Started
FEAT-002 | Timeline/story chapters | P0 | Feature | ARCH-001,ARCH-002,UX-001 | Not Started
FEAT-003 | Gallery and viewer | P0 | Feature | MEDIA-001,UX-001 | Not Started
FEAT-004 | Video and voice players | P0 | Feature | MEDIA-001,AUDIO-001 | Not Started
FEAT-005 | Quiz | P0 | Feature | ARCH-001,ARCH-002,UX-001 | Not Started
FEAT-006 | Letter and finale | P0 | Feature | ARCH-001,ARCH-002,UX-001 | Not Started
SEC-002 | Protected media, headers, metadata, direct-URL tests | P0 | Security | SEC-001,MEDIA-001 | Not Started
QA-001 | Automated P0 E2E and accessibility tests | P0 | QA | FEAT-001..006 | Not Started
CONTENT-001 | Integrate approved content and media manifest | P0 | Content/Media | ARCH-001,MEDIA-001 | Not Started
QA-002 | Real-device/UAT/production verification | P0 | QA/Owner | CONTENT-001,QA-001,SEC-002 | Not Started
REL-001 | Production promotion, DNS, rollback drill | P0 | Release | QA-002 | Not Started
P1-001 | Memory jar/reasons/future dreams/tap cake | P1 | Feature | P0 green | Not Started
RET-001 | Schedule and execute retirement/deletion | P0 | Owner | REL-001 | Not Started

## Requirements
Requirement ID | Type / Area | Description | Priority | UX Screen | Implementation Task | Test IDs | Status | Evidence
FR-001 | Functional - Access | The system shall deny story content until the configured access rule succeeds. | P0 |  |  |  | Baseline
FR-002 | Functional - Narrative lock | The experience shall accept Switzerland case-insensitively after trim/normalization. | P0 |  |  |  | Baseline
FR-003 | Functional - Audio consent | The system shall start music only after a user gesture and retain a visible mute control. | P0 |  |  |  | Baseline
FR-004 | Functional - Birthday state | The system shall derive countdown and celebration state using Asia/Kolkata unless configured otherwise. | P0 |  |  |  | Baseline
FR-005 | Functional - Story progression | The user shall navigate forward and backward using taps and gestures without losing progress. | P0 |  |  |  | Baseline
FR-006 | Functional - Deep-link safety | Protected internal routes shall not expose private copy or media when opened directly. | P0 |  |  |  | Baseline
FR-007 | Functional - Photo gallery | Photos shall support lazy loading, swipe, zoom, captions, and an accessible close action. | P0 |  |  |  | Baseline
FR-008 | Functional - Video playback | Opening video shall pause or duck background music and restore it after playback. | P0 |  |  |  | Baseline
FR-009 | Functional - Voice playback | Voice-note playback shall pause or duck background music and expose elapsed/duration state. | P0 |  |  |  | Baseline
FR-010 | Functional - Quiz | The quiz shall present one question at a time, normalize answers, and provide gentle retry feedback. | P0 |  |  |  | Baseline
FR-011 | Functional - Quiz completion | Completing all required questions shall unlock the next story section. | P0 |  |  |  | Baseline
FR-012 | Functional - Letter | The letter shall be readable without waiting for animation and respect reduced-motion settings. | P0 |  |  |  | Baseline
FR-013 | Functional - Finale | The finale shall provide a tap fallback for every sensor-based interaction. | P0 |  |  |  | Baseline
FR-014 | Functional - Progress persistence | The experience shall retain non-sensitive local progress across accidental refreshes. | P1 |  |  |  | Baseline
FR-015 | Functional - Content validation | Build shall fail when required content IDs, media references, or answer definitions are invalid. | P0 |  |  |  | Baseline
FR-016 | Functional - No indexing | Production shall use noindex/nofollow directives and generic social metadata. | P0 |  |  |  | Baseline
FR-017 | Functional - Error recovery | Media failures shall show an emotionally neutral retry/skip state rather than a broken page. | P0 |  |  |  | Baseline
FR-018 | Functional - Replay | The ending shall allow replay without requiring the user to re-enter personal answers unless configured. | P1 |  |  |  | Baseline
FR-019 | Functional - Admin-free content | All personalized content shall be file-driven and deployable without a database or CMS for this release. | P0 |  |  |  | Baseline
FR-020 | Functional - Deletion | The deployment owner shall be able to remove the site and media using a documented retirement procedure. | P0 |  |  |  | Baseline
NFR-001 | Non-functional - Performance | LCP <= 2.5 s at p75 on representative mobile production tests after the initial private gate. | P0 |  |  |  | Baseline
NFR-002 | Non-functional - Responsiveness | No horizontal overflow at 320, 360, 375, 390, 412, and 430 CSS px. | P0 |  |  |  | Baseline
NFR-003 | Non-functional - Accessibility | Target WCAG 2.2 AA for keyboard, contrast, names, focus, captions, reduced motion, and touch targets. | P0 |  |  |  | Baseline
NFR-004 | Non-functional - Privacy | Personal assets shall not be embedded in public source control or exposed before authorization. | P0 |  |  |  | Baseline
NFR-005 | Non-functional - Security | Secrets and access verification shall execute server-side; no plaintext passphrase in client bundles. | P0 |  |  |  | Baseline
NFR-006 | Non-functional - Reliability | Core story remains usable when audio, vibration, microphone, wake lock, or motion sensors are unavailable. | P0 |  |  |  | Baseline
NFR-007 | Non-functional - Compatibility | Support current Safari iOS and Chrome Android; graceful degradation on other modern browsers. | P0 |  |  |  | Baseline
NFR-008 | Non-functional - Maintainability | Typed content, stable IDs, lint/type/test gates, and documented agent handoffs are mandatory. | P0 |  |  |  | Baseline
NFR-009 | Non-functional - Media efficiency | Images shall be resized and encoded to AVIF/WebP with a JPEG fallback; video shall use phone-friendly MP4. | P0 |  |  |  | Baseline
NFR-010 | Non-functional - Observability | Production shall expose privacy-safe operational errors without collecting story answers or personal content. | P1 |  |  |  | Baseline
NFR-011 | Non-functional - Motion safety | Non-essential motion shall be disabled or simplified under prefers-reduced-motion. | P0 |  |  |  | Baseline
NFR-012 | Non-functional - Asset integrity | A build-time manifest shall detect missing and orphaned media. | P0 |  |  |  | Baseline

## Media Inventory
asset_id | source_filename | kind | album_or_chapter | captured_at | order | people_shown | caption | alt_text | object_position | sensitive | rights_status | consent_status | approval_status | original_checksum | derivative_path | poster_path | duration_seconds | width | height | notes
unassigned-source-image-01 | 2515b62c-ecce-4563-b74f-e2586568e32b.png | image | [6 empty] | 50% 50% |  | unknown | unknown | missing | [6 empty] | Referenced in source; binary not received
unassigned-source-image-02 | 5619d1a0-5a19-41b9-acba-c7ab3d376585.png | image | [6 empty] | 50% 50% |  | unknown | unknown | missing | [6 empty] | Referenced in source; binary not received
unassigned-source-image-03 | 91eeed48-942a-4321-81ad-978305bb719a.png | image | [6 empty] | 50% 50% |  | unknown | unknown | missing | [6 empty] | Referenced in source; binary not received
unassigned-source-image-04 | 52a80496-d17f-4fb8-a479-263dc228850d.png | image | [6 empty] | 50% 50% |  | unknown | unknown | missing | [6 empty] | Referenced in source; binary not received

## Content Approvals
content_id | content_type | exact_text_or_summary | source | owner | status | approver | approved_at | affected_screen | notes
fact-birthday | fact | 8 August 2026 | source baseline | Project Owner | Confirmed |  |  | S05
fact-first-message | fact | 19 December 2025 | source baseline | Project Owner | Confirmed |  |  | S06/S10
fact-committed | fact | 26 December 2025 at 6:12 PM | source baseline | Project Owner | Confirmed |  |  | S06/S10
fact-first-meet | fact | 6 January 2026 at 4:20 AM | source baseline | Project Owner | Confirmed |  |  | S06/S10
fact-location | fact | Krishnarajapuram Railway Station, Bengaluru | source baseline | Project Owner | Confirmed |  |  | S06
fact-destination | fact | Switzerland | source baseline | Project Owner | Confirmed |  |  | S02/S10/S13
copy-letter | letter | Client input required |  | Client | Open |  |  | S14
copy-finale | finale | Client input required |  | Client | Open |  |  | S16/S17

## Risks
Risk ID | Risk | Likelihood | Impact | Score | Mitigation | Owner | Trigger | Contingency | Status | Review Date
R-01 | Late or disorganized media | High | High | 9 | Freeze media by 5 Aug; use inventory sheet and deterministic filenames. |  |  |  | Open
R-02 | Copyrighted music without rights | High | High | 9 | Use licensed/royalty-free instrumental or client-supplied authorized track. |  |  |  | Open
R-03 | Private photos exposed publicly | High | Critical | 12 | Server-side gate, non-public storage where feasible, noindex, generic metadata, retirement date. |  |  |  | Open
R-04 | Heavy media causes slow load | High | High | 9 | Transcode, lazy-load, poster frames, prefetch only adjacent assets, bundle budgets. |  |  |  | Open
R-05 | Autoplay blocked | Certain | Medium | 8 | Explicit start gesture; persistent music control; never rely on autoplay. |  |  |  | Open
R-06 | Sensor APIs unavailable | High | Low | 3 | Tap fallback for candle and gift; progressive enhancement only. |  |  |  | Open
R-07 | Too many animations | Medium | High | 6 | Use Motion + CSS only; define motion budget; reduced-motion mode. |  |  |  | Open
R-08 | Scope growth near deadline | High | High | 9 | P0 freeze 6 Aug 18:00 IST; defer P2 without destabilizing P0. |  |  |  | Open
R-09 | Incorrect personal facts/copy | Medium | High | 6 | Client sign-off matrix for dates, names, answers, letter, captions. |  |  |  | Open
R-10 | AI agents overwrite working code | Medium | High | 6 | Small tasks, protected ownership, tests before/after, mandatory handoff. |  |  |  | Open
R-11 | Repository contains personal assets | Medium | Critical | 8 | Gitignore media, use private artifact channel, secret scan before push. |  |  |  | Open
R-12 | Timezone bug changes countdown | Medium | Medium | 4 | Use explicit Asia/Kolkata and test boundaries around midnight. |  |  |  | Open

## Test Evidence
test_id | build_id | deployment_url_private | device | os | browser | viewport | network | expected | observed | result | tester | tested_at | evidence_location | notes

## Release Checklist
Gate | Checklist Item | Owner | Status | Evidence | Notes
Content | All personal facts and exact copy approved | Client / Owner | Not Started
Content | All media approved, ordered, captioned, and rights-confirmed | Client / Media | Not Started
Engineering | Lint, typecheck, tests, content validation, production build pass | Orchestrator | Not Started
Engineering | P0 complete; unstable optional features removed | Orchestrator | Not Started
Privacy | Unauthorized routes/assets/previews blocked | Security | Not Started
Privacy | Generic metadata, noindex, secrets/logs/repository audited | Security | Not Started
Experience | Real iPhone Safari and Android Chrome complete journey | QA | Not Started
Experience | Reduced motion, sound off, error recovery, safe areas pass | QA | Not Started
Release | Client UAT approved exact deployment | Client | Not Started
Release | Production domain/TLS and clean-device verification pass | Release Owner | Not Started
Release | Rollback rehearsed and owner available | Release Owner | Not Started
Lifecycle | Retirement date/owner scheduled | Project Owner | Not Started

## Daily Plan
Date | Focus | Planned Exit Criteria | Owner | Status | Blockers / Notes
2026-08-02 | Requirements, repository, CI, client input request | Project builds; inputs requested | Owner / Orchestrator | Not Started
2026-08-03 | Foundation, access/media architecture, interfaces | Interfaces and protection option frozen | Engineering / Security | Not Started
2026-08-04 | P0 story spine and media pipeline | Synthetic core journey works | Feature / Media | Not Started
2026-08-05 | Gallery, video, voice, quiz, letter, finale | P0 integrated; media cutoff | Feature / Content | Not Started
2026-08-06 | Content, resilience, accessibility, performance | Protected preview; P0 freeze 18:00 | All | Not Started
2026-08-07 | Real-device UAT, production, DNS, rollback | Written approval; production verified | QA / Release | Not Started
2026-08-08 | Monitoring only | Experience available; rollback ready | Owner / Release | Not Started

## Decision Log
Decision ID | Date | Owner | Context | Options | Decision | Consequences | Requirement IDs | Review / Expiry
D-01 | 2026-08-02 | Architecture | Story navigation | Route per screen ¦ State-driven shell | State-driven shell | Central audio, privacy, transitions | FR-005,NFR-008
D-02 | 2026-08-02 | Architecture | Animation stack | Motion only ¦ Motion + GSAP | Motion + CSS only | Lower bundle and complexity | NFR-001,NFR-011
D-03 | 2026-08-02 | Security | Narrative answer security | Client-only ¦ Server access | Server/managed access; answer narrative | Protects content and assets | FR-001,NFR-004,NFR-005 | Finalize provider option
D-04 | 2026-08-02 | Product | Content storage | CMS/DB ¦ Typed files | Typed file-based content | Fast, auditable fixed-scope delivery | FR-019,NFR-008

## References
Topic | Official URL | Why it matters | Checked date
Next.js releases/security | https://nextjs.org/blog | Select supported patched framework version | 2026-08-02
React versions | https://react.dev/versions | Confirm supported React line | 2026-08-02
Node.js releases | https://nodejs.org/en/about/previous-releases | Use production LTS runtime | 2026-08-02
Tailwind releases | https://tailwindcss.com/blog | Confirm current styling tool version | 2026-08-02
WCAG 2.2 | https://www.w3.org/TR/WCAG22/ | Accessibility target | 2026-08-02
Vercel deployment protection | https://vercel.com/docs/security/deployment-protection | Evaluate access protection plan/features | 2026-08-02